## Sheet1
Issue/Synopsis:Compressor surge.
Customer reported that RH engine experienced a compressor surge.
Troubleshooting: Troubleshooting performed as per EMM with no
findings. P2.5 switching valve inspected with no findings. IBV
EEC | were replaced with no improvement. BSI performed with no
defects. Performance run also completed with bleed capped and
found all parameters are within limits and no stall in capped
Run. . .
Resolution: Engine and AF Harnesses replaced. RTS'ed and under
monitoring for further anomalies
engine and A/F harness was replaced
TQ | Nh and Nl); which concur with the fuel regulation
issue.MFCU replaced and engine runs performed with no
anomalies. A/C RTS
ATR reviewed QAR
4-Nov-21 STM: send the event details and QAR to Porto and JF
and Wesley. Keep open
18-Nov-21 STM: raise ECN RFA MFCU
9-Dec-21 STM: Send details to Wesley for part details follow up
14-Apr-22 STM: Keep it open.
21-Apr-22 STM : will review report in next week
28-Apr-22 STM: confirm issue reoccurred?. Send QAR to Porto
5-May-22 STM: keep it open. Going to review with engineering.
Send report to JF
26-May-22 STM: send reminder to JF for report update
Note: . TSN/TCSN as of Jun-2021.
Troubleshooting: .
Resolution: .