## Register (hidden)
Drawing Register and Drawing Log for ICH
LEGEND |  |  | DATE:
MEINHARDT=Meinhardt (Singapore) Pte Ltd
CHECK/CODE | DRAW BY | GROUP | REVISION | ISSUE DATE | ISSUE FOR | REMARK
STRUCTURE DRAWING | MEINHARDT | CONSTRUCTION SEQUENCE
CAPPING BEAM REBAR DETAIL
GENERAL NOTE
MEINHARD STRUCTURE
SHOP DRAWING |  | CAPPING BEAM SHOP DRAWING
B1 SHOP DRAWING
B2 SHOP DRAWING
L1 SHOP DRAWING
ST01 AND ST05
CRA-DWG-S-031/042
CRA-DWG-S-024
CRA-DWG-S-040
* For the drawing detail please refer to the each discipline drawing log at behind.

## ARCHI DRAWING
ISSUE FOR APPROVAL
ISSUE FOR CONSTRUCTION
REJECT WITH COMMENTS
| Project: | JTC CLEANTECH 2B
ARCHI DRAWING
S/N | DRAWING NO. | DRAWING DESCRIPTION | SCALE | SIZE | ISSUE DATE | [6 empty] | REMARK
[5 empty] | TENDER | REV. 0 | REV.1 | REV.2 | REV.3 | REV.4 | REV.5
1
| 1 3 | 1 7 | 1 8 | 1 9
| 1 3 | 1 7 | 1 8 | 1 9
| 1 3 | 1 7 | 1 8 | 1 9
| 1 3 | 1 7 | 1 8 | 1 9
| P306479_A-FE-401 P306479_A-FE-402 P306479_A-FE-403 | ELEVATIONS ELEVATION 1 & 2 ELEVATION 3 & 4 ELEVATION 5 | 1:200 1:200 1:200 | A1 A1 A1
| P306479_A-FX-501 | SECTIONS SECTION 1, 2 & 3 | 1:200 | A1
| P306479_A-EP-701 P306479_A-EP-702 P306479_A-EP-720 P306479_A-EP-721 P306479_A-EP-722 P306479_A-EP-723 P306479_A-EP-724 P306479_A-EP-725 P306479_A-EP-726 P306479_A-EP-727 P306479_A-EP-750 P306479_A-EP-751 P306479_A-EP-752 P306479_A-EP-753 P306479_A-EP-760 P306479_A-EP-761 P306479_A-EP-770 P306479_A-SCH-1001 P306479_A-SCH-1002 | ENLARGED PLAN TOILET PLANS 1ST STOREY MALE, FEMALE & HANDICAPPED TOILET PLAN TYPICAL TOILET (MALE, FEMALE & HANDICAP) - 1ST MEZZANINE TO 4TH STOREY STAIRCASE PLAN STAIRCASE 1 PLANS - BASEMENT TO 2ND STOREY - PART 1 STAIRCASE 1 PLANS - 2ND STOREY MEZZ TO LOWER ROOF- PART 2 STAIRCASE 1 - SECTION A STAIRCASE 1 - SECTION B STAIRCASE 2 PLANS - BASEMENT TO 2ND STOREY - PART 1 STAIRCASE 2 PLANS - 2ND STOREY MEZZ TO LOWER ROOF- PART 2 STAIRCASE 2 - SECTION A STAIRCASE 2 - SECTION B LIFT LOBBY LIFT LOBBY - PLANS AND ELEVATION LIFT LOBBY - PERSPECTIVE VIEWS PLAN AND SECTION THRU PASSENGER LIFT HOISTWAY PLAN AND SECTION THRU SERVICE LIFT HOISTWAY, PLATFORM LIFT AND SCISSOR LIFT ELECTRICAL SUB-STATION ELECTRICAL SUB-STATION - PLAN AND ELEVATION ELECTRICAL SUB-STATION - SECTIONS AND ELEVATION BIN CENTRE BIN CENTRE - PLAN AND SECTIONS SCHEDULES WINDOW SCHEDULE - 1 WINDOW SCHEDULE - 2 | 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 1:50 NTS 1:50 1:50 1:50 1:50 1:50 NTS NTS | A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1 A1
A3 DRAWINGS
| P306479_A-PW-1200 P306479_A-PW-1201 | WALL TYPES | AS SHOWN AS SHOWN
|  | WALL TYPES AND DETAILS TYPICAL COMM/MMR/LAN ROOM INSULATION LAYOUT PLAN AND SECTIONS |  | A3 A3
| P306479_A-PW-1250 P306479_A-PW-1251 P306479_A-PW-1252 P306479_A-PW-1253 P306479_A-PW-1254 P306479_A-PW-1255 P306479_A-PW-1256 P306479_A-PW-1257 | KEY PLAN OF FIRE RATED WALL COMPARTMENTATION KEYPLAN FOR FIRE COMPARTMENTATION - BASEMENT PLAN KEYPLAN FOR FIRE COMPARTMENTATION - 1ST STOREY PLAN KEYPLAN FOR FIRE COMPARTMENTATION -1ST STOREY MEZZANINE PLAN KEYPLAN FOR FIRE COMPARTMENTATION - 2ND STOREY PLAN KEYPLAN FOR FIRE COMPARTMENTATION - 2ND STOREY MEZZANINE PLAN KEYPLAN FOR FIRE COMPARTMENTATION - 3RD STOREY PLAN KEYPLAN FOR FIRE COMPARTMENTATION - 4TH STOREY PLAN KEYPLAN FOR FIRE COMPARTMENTATION - ROOF PLAN | 1:300 1:300 1:300 1:300 1:300 1:300 1:300 1:300 | A3 A3 A3 A3 A3 A3 A3 A3

## STRUCTURE DRAWING
ISSUE FOR CONSTRUCTION
REJECT WITH COMMENTS
| Project: | JTC CLEANTECH 2B
STRUCTURE DRAWING
S/N | DRAWING NUMBER |  |  |  | REMARK
2 | 1 3
3 | 1 3
4 | 1 3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
| 1 7 | 1 8 | 1 9

## M&E DRAWING
ISSUE FOR APPROVAL
ISSUE FOR CONSTRUCTION
REJECT WITH COMMENTS
| Project: | JTC CLEANTECH 2B
M&E DRAWING
S/N | DRAWING NO. | DRAWING DESCRIPTION | SCALE | SIZE | ISSUE DATE | [6 empty] | REMARK
[5 empty] | TENDER | REV. 0 | REV.1 | REV.2 | REV.3 | REV.4 | REV.5
ACMV
1 | CT2B-M-0001 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - SITE PLAN & LOCATION PLAN | As Shown | A1
2 | CT2B-M-0100 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - DRAWING LIST | NTS | A1
3 | CT2B-M-0101 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - GENERAL NOTES | NTS
4 | CT2B-M-0102 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - LEGENDS | NTS
5 | CT2B-M-0201 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - STANDARD DETAILS 1 | NTS
6 | CT2B-M-0202 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - STANDARD DETAILS 2 | NTS
7 | CT2B-M-0203 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - SECTION DETAILS | 1 : 50
8 | CT2B-M-1B10 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - BASEMENT 1 OVERALL PLAN | 1 : 200
9 | CT2B-M-1B11 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - BASEMENT 1 PLAN (PART 1 OF 2) | 1 : 150
10 | CT2B-M-1B12 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - BASEMENT 1 PLAN (PART 2 of 2) | 1 : 150
11 | CT2B-M-1010 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 1ST STOREY OVERALL PLAN | 1 : 200
12 | CT2B-M-1011 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 1ST STOREY PLAN (PART 1 OF 2) | 1 : 150
13 | CT2B-M-1012 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 1ST STOREY PLAN (PART 2 of 2) | 1 : 150
14 | CT2B-M-1M10 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 1ST STOREY MEZZANINE PLAN | 1 : 150
15 | CT2B-M-1020 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 2ND STOREY PLAN | 1 : 150
16 | CT2B-M-1021 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 2ND STOREY PLAN (CT2) CHILLED AND CONDENSATE WATER PIPING | 1 : 150
17 | CT2B-M-1M20 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 2ND STOREY MEZZANINE PLAN | 1 : 150
18 | CT2B-M-1030 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 3RD STOREY PLAN | 1 : 150
19 | CT2B-M-1040 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - 4TH STOREY PLAN | 1 : 150
20 | CT2B-M-1LR0 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - LOWER ROOF PLAN | 1 : 150
21 | CT2B-M-1UR0 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - UPPER ROOF PLAN | 1 : 150
22 | CT2B-M-7101 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - CHILLED WATER SCHEMATIC DIAGRAM (BASE) | NTS
23 | CT2B-M-7102 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - MECHANICAL VENTILATION SYSTEM SCHEMATIC DIAGRAM | NTS
24 | CT2B-M-7103 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - EQUIPMENT SCHEDULE | NTS
25 | CT2B-M-7104 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - BMS SCHEMATIC DIAGRAM | NTS
26 | CT2B-M-7105 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - CHILLED WATER SCHEMATIC DIAGRAM (OPTIONAL) | NTS
27 | CT2B-M-7106 | AIRCONDITIONING & MECHANICAL VENTILATION SYSTEM - MCC SINGLE LINE DIAGRAM | NTS
PLUMBING & SANITARY
1 | CT4-P-0001 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - SITE AND LOCATION PLAN
2 | CT4-P-0100 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - DRAWING LIST
3 | CT4-P-0101 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - NOTES AND LEGENDS
4 | CT4-P-0201 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - STANDARD DETAILS 1
5 | CT4-P-0202 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - STANDARD DETAILS 2
6 | CT4-P-0203 | SANITARY, PLUMBING & DRAINAGE INSTALLATION WATER RETICULATION SYSTEM - STANDARD DETAILS 3
7 | CT4-P-1B10 | WATER RETICULATION SYSTEM - BASEMENT 1 OVERALL PLAN
8 | CT4-P-1B11 | WATER RETICULATION SYSTEM - BASEMENT 1 PLAN (PART 1 OF 2)
9 | CT4-P-1B12 | WATER RETICULATION SYSTEM - BASEMENT 1 PLAN (PART 2 of 2)
10 | CT4-P-1010 | WATER RETICULATION SYSTEM - 1ST STOREY OVERALL PLAN
11 | CT4-P-1011 | WATER RETICULATION SYSTEM - 1ST STOREY PLAN (PART 1 OF 2)
12 | CT4-P-1012 | WATER RETICULATION SYSTEM - 1ST STOREY PLAN (PART 2 of 2)
13 | CT4-P-1M10 | WATER RETICULATION SYSTEM - 1ST STOREY MEZZANINE PLAN
14 | CT4-P-1020 | WATER RETICULATION SYSTEM - 2ND STOREY PLAN
15 | CT4-P-1M20 | WATER RETICULATION SYSTEM - 2ND STOREY MEZZANINE PLAN
16 | CT4-P-1030 | WATER RETICULATION SYSTEM - 3RD STOREY PLAN
17 | CT4-P-1040 | WATER RETICULATION SYSTEM - 4TH STOREY PLAN
18 | CT4-P-1LR0 | WATER RETICULATION SYSTEM - LOWER ROOF PLAN
19 | CT4-P-7101 | WATER RETICULATION SYSTEM - SCHEMATIC DIAGRAM
20 | CT4-P-2B10 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - BASEMENT 1 OVERALL PLAN
21 | CT4-P-2B11 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - BASEMENT 1 PLAN (PART 1 OF 2)
22 | CT4-P-2B12 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - BASEMENT 1 PLAN (PART 2 of 2)
23 | CT4-P-2010 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 1ST STOREY OVERALL PLAN
24 | CT4-P-2011 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 1ST STOREY PLAN (PART 1 OF 2)
25 | CT4-P-2012 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 1ST STOREY PLAN (PART 2 of 2)
26 | CT4-P-2M10 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 1ST STOREY MEZZANINE PLAN
27 | CT4-P-2020 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 2ND STOREY PLAN
28 | CT4-P-2M20 | WATER RETICULATION SYSTEM - 2ND STOREY MEZZANINE PLAN
29 | CT4-P-2030 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 3RD STOREY PLAN
30 | CT4-P-2040 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - 4TH STOREY PLAN
31 | CT4-P-2LR0 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - LOWER LOWER ROOF PLAN
32 | CT4-P-7201 | SANITARY, PLUMBING & DRAINAGE INSTALLATION - SCHEMATIC DIAGRAM
FIRE PROTECTION SYSTEM
1 | CT2B-F-0001 | FIRE PROTECTION SYSTEM - SITE AND LOCATION PLAN
2 | CT2B-F-0100 | FIRE PROTECTION SYSTEM - DRAWING LIST
3 | CT2B-F-0101 | FIRE PROTECTION SYSTEM - NOTES & LEGENDS
4 | CT2B-F-0201 | FIRE PROTECTION SYSTEM - STANDARD DETAILS 1
5 | CT2B-F-0202 | FIRE PROTECTION SYSTEM - STANDARD DETAILS 2
6 | CT2B-F-1B10 | FIRE PROTECTION SYSTEM - BASEMENT 1 OVERALL PLAN
7 | CT2B-F-1B11 | FIRE PROTECTION SYSTEM - BASEMENT 1 PLAN (PART 1 OF 2)
8 | CT2B-F-1B12 | FIRE PROTECTION SYSTEM - BASEMENT 1 PLAN (PART 2 of 2)
9 | CT2B-F-1010 | FIRE PROTECTION SYSTEM - 1ST STOREY OVERALL PLAN
10 | CT2B-F-1011 | FIRE PROTECTION SYSTEM - 1ST STOREY PLAN (PART 1 OF 2)
11 | CT2B-F-1012 | FIRE PROTECTION SYSTEM - 1ST STOREY PLAN (PART 2 of 2)
12 | CT2B-F-1M10 | FIRE PROTECTION SYSTEM - 1ST STOREY MEZZANINE PLAN
13 | CT2B-F-1020 | FIRE PROTECTION SYSTEM - 2ND STOREY PLAN
14 | CT2B-F-1M20 | FIRE PROTECTION SYSTEM - 2ND STOREY MEZZANINE PLAN
15 | CT2B-F-1030 | FIRE PROTECTION SYSTEM - 3RD STOREY PLAN
16 | CT2B-F-1040 | FIRE PROTECTION SYSTEM - 4TH STOREY PLAN
17 | CT2B-F-1LR0 | FIRE PROTECTION SYSTEM - LOWER ROOF PLAN
18 | CT2B-F-7101 | FIRE PROTECTION SYSTEM - AUTOMATIC SPRINKLER SYSTEM SCHEMATIC DIAGRAM
19 | CT2B-F-7102 | FIRE PROTECTION SYSTEM - FIRE HOSEREEL SYSTEM, DRY RISING MAIN SYSTEM AND FIRE HYDRANT SCHEMATIC DIAGRAM
20 | CT2B-F-7103 | FIRE PROTECTION SYSTEM - AUTOMATIC FIRE ALARM SYSTEM AND FIREMAN INTERCOM SYSTEM SCHEMATIC DIAGRAM
ELECTRICAL INSTALLATION
1 | CT2B-E-0001 | ELECTRICAL INSTALLATION- SITE & LOCATION PLAN
2 | CT2B-E-0100 | ELECTRICAL INSTALLATION- DRAWING LIST
3 | CT2B-E-0101 | ELECTRICAL INSTALLATION- GENERAL NOTES 1
4 | CT2B-E-0102 | ELECTRICAL INSTALLATION- GENERAL NOTES 2
5 | CT2B-E-0103 | ELECTRICAL INSTALLATION- LEGEND
6 | CT2B-E-0201 | ELECTRICAL INSTALLATION- STANDARD DETAILS 1
7 | CT2B-E-0202 | ELECTRICAL INSTALLATION- STANDARD DETAILS 2
8 | CT2B-E-0203 | ELECTRICAL INSTALLATION- STANDARD DETAILS 3
9 | CT2B-E-0204 | ELECTRICAL INSTALLATION- STANDARD DETAILS 4
10 | CT2B-E-0205 | ELECTRICAL INSTALLATION- STANDARD DETAILS 5
11 | CT2B-E-0206 | ELECTRICAL INSTALLATION- STANDARD DETAILS 6
12 | CT2B-E-0207 | ELECTRICAL INSTALLATION- STANDARD DETAILS 7
13 | CT2B-E-0301 | ELECTRICAL INSTALLATION- FUEL SYSTEM - LAYOUT & SCHEMATIC DIAGRAM
LIGHTING LAYOUT
14 | CT2B-E-1B10 | ELECTRICAL INSTALLATION- LIGHTING BASEMENT 1 LAYOUT - OVERALL PLAN
15 | CT2B-E-1B11 | ELECTRICAL INSTALLATION- LIGHTING BASEMENT 1 LAYOUT (PART 1 OF 2)
16 | CT2B-E-1B12 | ELECTRICAL INSTALLATION- LIGHTING BASEMENT 1 LAYOUT (PART 2 OF 2)
17 | CT2B-E-1010 | ELECTRICAL INSTALLATION - LIGHTING 1ST STOREY LAYOUT - OVERALL PLAN
18 | CT2B-E-1011 | ELECTRICAL INSTALLATION - LIGHTING 1ST STOREY LAYOUT (PART 1 OF 2)
19 | CT2B-E-1012 | ELECTRICAL INSTALLATION - LIGHTING 1ST STOREY LAYOUT (PART 2 OF 2)
20 | CT2B-E-1M10 | ELECTRICAL INSTALLATION- LIGHTING: 1ST STOREY MEZZANINE LAYOUT
21 | CT2B-E-1020 | ELECTRICAL INSTALLATION- LIGHTING: 2ND STOREY LAYOUT
22 | CT2B-E-1M20 | ELECTRICAL INSTALLATION- LIGHTING: 2ND STOREY MEZZANINE LAYOUT
23 | CT2B-E-1030 | ELECTRICAL INSTALLATION- LIGHTING: 3RD STOREY LAYOUT
24 | CT2B-E-1040 | ELECTRICAL INSTALLATION- LIGHTING: 4TH STOREY LAYOUT
25 | CT2B-E-1LR0 | ELECTRICAL INSTALLATION- LIGHTING: LOWER ROOF LAYOUT
26 | CT2B-E-1UR0 | ELECTRICAL INSTALLATION- LIGHTING: UPPER ROOF LAYOUT
POWER LAYOUT
27 | CT2B-E-2B10 | ELECTRICAL INSTALLATION- POWER : BASEMENT 1 LAYOUT - OVERALL PLAN
28 | CT2B-E-2B11 | ELECTRICAL INSTALLATION- POWER : BASEMENT 1 LAYOUT (PART 1 OF 2)
29 | CT2B-E-2B12 | ELECTRICAL INSTALLATION- POWER : BASEMENT 1 LAYOUT (PART 2 OF 2)
30 | CT2B-E-2010 | ELECTRICAL INSTALLATION - POWER : 1ST STOREY LAYOUT - OVERALL PLAN
31 | CT2B-E-2011 | ELECTRICAL INSTALLATION - POWER : 1ST STOREY LAYOUT (PART 1 OF 2)
32 | CT2B-E-2012 | ELECTRICAL INSTALLATION - POWER : 1ST STOREY LAYOUT (PART 2 OF 2)
33 | CT2B-E-2M10 | ELECTRICAL INSTALLATION- POWER : 1ST STOREY MEZZANINE LAYOUT
34 | CT2B-E-2020 | ELECTRICAL INSTALLATION- POWER : 2ND STOREY LAYOUT
35 | CT2B-E-2M20 | ELECTRICAL INSTALLATION- POWER : 2ND STOREY MEZZANINE LAYOUT
36 | CT2B-E-2030 | ELECTRICAL INSTALLATION- POWER : 3RD STOREY LAYOUT
37 | CT2B-E-2040 | ELECTRICAL INSTALLATION- POWER : 4TH STOREY LAYOUT
38 | CT2B-E-2LR0 | ELECTRICAL INSTALLATION- POWER : LOWER ROOF LAYOUT
LIGHTNING PROTECTION LAYOUT
39 | CT2B-E-3B10 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : BASEMENT 1 LAYOUT
40 | CT2B-E-3010 | ELECTRICAL INSTALLATION - LIGHTNING PROTECTION : 1ST STOREY LAYOUT
41 | CT2B-E-3M10 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : 1ST STOREY MEZZANINE LAYOUT
42 | CT2B-E-3020 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : 2ND STOREY LAYOUT
43 | CT2B-E-3M20 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : 2ND STOREY MEZZANINE LAYOUT
44 | CT2B-E-3030 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : 3RD STOREY LAYOUT
45 | CT2B-E-3040 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : 4TH STOREY LAYOUT
46 | CT2B-E-3LR0 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : LOWER ROOF LAYOUT
47 | CT2B-E-3UR0 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : UPPER ROOF LAYOUT
48 | CT2B-E-7030 | ELECTRICAL INSTALLATION- LIGHTNING PROTECTION : ELEVATIONS A. B, C, & D
SECURITY LAYOUT
49 | CT2B-E-4B10 | ELECTRICAL INSTALLATION- SECURITY : BASEMENT 1 LAYOUT
50 | CT2B-E-4010 | ELECTRICAL INSTALLATION - SECURITY : 1ST STOREY LAYOUT
51 | CT2B-E-4M10 | ELECTRICAL INSTALLATION- SECURITY : 1ST STOREY MEZZANINE LAYOUT
52 | CT2B-E-4020 | ELECTRICAL INSTALLATION- SECURITY : 2ND STOREY LAYOUT
53 | CT2B-E-4M20 | ELECTRICAL INSTALLATION- SECURITY : 2ND STOREY MEZZANINE LAYOUT
54 | CT2B-E-4030 | ELECTRICAL INSTALLATION- SECURITY : 3RD STOREY LAYOUT
55 | CT2B-E-4040 | ELECTRICAL INSTALLATION- SECURITY : 4TH STOREY LAYOUT
56 | CT2B-E-4LR0 | ELECTRICAL INSTALLATION- SECURITY : LOWER ROOF LAYOUT
EMERGENCY VOICE COMMUNICATION
57 | CT2B-E-5B10 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : BASEMENT 1 LAYOUT
58 | CT2B-E-5010 | ELECTRICAL INSTALLATION - EMERGENCY VOICE COMMUNICATION : 1ST STOREY LAYOUT
59 | CT2B-E-5M10 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : 1ST STOREY MEZZANINE LAYOUT
60 | CT2B-E-5020 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : 2ND STOREY LAYOUT
61 | CT2B-E-5M20 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : 2ND STOREY MEZZANINE LAYOUT
62 | CT2B-E-5030 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : 3RD STOREY LAYOUT
63 | CT2B-E-5040 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : 4TH STOREY LAYOUT
64 | CT2B-E-5LR0 | ELECTRICAL INSTALLATION- EMERGENCY VOICE COMMUNICATION : LOWER ROOF LAYOUT
CABLE CONTAINMENT
65 | CT2B-E-6B10 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : BASEMENT 1 LAYOUT - OVERALL PLAN
66 | CT2B-E-6B11 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : BASEMENT 1 LAYOUT (PART 1 OF 2)
67 | CT2B-E-6B12 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : BASEMENT 1 LAYOUT (PART 2 OF 2)
68 | CT2B-E-6010 | ELECTRICAL INSTALLATION - CABLE CONTAINMENT : 1ST STOREY LAYOUT - OVERALL PLAN
69 | CT2B-E-6011 | ELECTRICAL INSTALLATION - CABLE CONTAINMENT : 1ST STOREY LAYOUT (PART 1 OF 2)
70 | CT2B-E-6012 | ELECTRICAL INSTALLATION - CABLE CONTAINMENT : 1ST STOREY LAYOUT (PART 2 OF 2)
71 | CT2B-E-6M10 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : 1ST STOREY MEZZANINE LAYOUT
72 | CT2B-E-6020 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : 2ND STOREY LAYOUT
73 | CT2B-E-6M20 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : 2ND STOREY MEZZANINE LAYOUT
74 | CT2B-E-6030 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : 3RD STOREY LAYOUT
75 | CT2B-E-6040 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : 4TH STOREY LAYOUT
76 | CT2B-E-6LR0 | ELECTRICAL INSTALLATION- CABLE CONTAINMENT : LOWER ROOF LAYOUT
SINGLE LINE DIAGRAM
77 | CT2B-E-7100 | ELECTRICAL INSTALLATION- MAIN SINGLE LINE DIAGRAM
78 | CT2B-E-7101 | ELECTRICAL INSTALLATION- HVSB MAIN SINGLE LINE DIAGRAM
79 | CT2B-E-7102A | ELECTRICAL INSTALLATION- MSB 1- SINGLE LINE DIAGRAM SHEET 1 OF 2
80 | CT2B-E-7102B | ELECTRICAL INSTALLATION- MSB 1- SINGLE LINE DIAGRAM SHEET 2 OF 2
81 | CT2B-E-7103 | ELECTRICAL INSTALLATION- EMSB - POWER SINGLE LINE DIAGRAM
82 | CT2B-E-7104 | ELECTRICAL INSTALLATION- SSB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM
83 | CT2B-E-7105 | ELECTRICAL INSTALLATION- DB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM 1
84 | CT2B-E-7106 | ELECTRICAL INSTALLATION- DB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM 2
85 | CT2B-E-7107 | ELECTRICAL INSTALLATION- EDB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM 1
86 | CT2B-E-7108 | ELECTRICAL INSTALLATION- EDB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM 2
87 | CT2B-E-7109 | ELECTRICAL INSTALLATION- EDB FOR COMMS SINGLE LINE DIAGRAM
88 | CT2B-E-7110 | ELECTRICAL INSTALLATION- MDF / MDS SINGLE LINE DIAGRAM
89 | CT2B-E-7111 | ELECTRICAL INSTALLATION- ESB FOR LIGHTING & SMALL POWER SINGLE LINE DIAGRAM
90 | CT2B-E-7112 | ELECTRICAL INSTALLATION- LIFT / OG BOX - SINGLE LINE DIAGRAM
91 | CT2B-E-7113 | ELECTRICAL INSTALLATION- MECHANICAL POWER - SINGLE LINE DIAGRAM
92 | CT2B-E-7114 | ELECTRICAL INSTALLATION- FCC ROOM - SINGLE LINE DIAGRAM
93 | CT2B-E-7115 | ELECTRICAL INSTALLATION- TENANT MOTOR PANEL - SINGLE LINE DIAGRAM
94 | CT2B-E-7116 | ELECTRICAL INSTALLATION- MMR - SINGLE LINE DIAGRAM
SCHEMATIC DIAGRAM
95 | CT2B-E-7201 | ELECTRICAL INSTALLATION- TELECOMMUNICATION SYSTEM SCHEMATIC DIAGRAM
96 | CT2B-E-7202 | ELECTRICAL INSTALLATION- CATV SYSTEM SCHEMATIC DIAGRAM
97 | CT2B-E-7203 | ELECTRICAL INSTALLATION- STRUCTURED CABLING SYSTEM SCHEMATIC DIAGRAM
98 | CT2B-E-7204 | ELECTRICAL INSTALLATION- PUBLIC ADDRESS (PA) AND EMERGENCY VOICE COMMUNICATION (EVC) SYSTEM SCHEMATIC DIAGRAM
99 | CT2B-E-7205 | ELECTRICAL INSTALLATION: PWD HOLDING POINT TWO-WAY VOICE COMMUNICATION SYSTEM SCHEMATIC DIAGRAM
100 | CT2B-E-7206 | ELECTRICAL INSTALLATION - EMERGENCY CALL BELL SYSTEM FOR HANDICAPPED TOILETS SCHEMATIC DIAGRAM
101 | CT2B-E-7207 | ELECTRICAL INSTALLATION: CARD ACCESS SYSTEM SCHEMATIC DIAGRAM SHEET 1
102 | CT2B-E-7208 | ELECTRICAL INSTALLATION: CARD ACCESS SYSTEM SCHEMATIC DIAGRAM SHEET 2
103 | CT2B-E-7209 | ELECTRICAL INSTALLATION - EARTHING SYSTEM SCHEMATIC DIAGRAM
104 | CT2B-E-7210 | ELECTRICAL INSTALLATION - CLEAN EARTHING SYSTEM SCHEMATIC DIAGRAM
105 | CT2B-E-7211 | ELECTRICAL INSTALLATION: LIGHT MANAGEMENT SYSTEM SCHEMATIC DIAGRAM
VERTICAL TRANSPORTATION INSTALLATION
106 | CT2B-K-1B10 | VERTICAL TRANSPORTATION INSTALLATION- BASEMENT 1 LAYOUT
107 | CT2B-K-1010 | VERTICAL TRANSPORTATION INSTALLATION - 1ST STOREY LAYOUT
108 | CT2B-K-1M10 | VERTICAL TRANSPORTATION INSTALLATION - 1ST STOREY MEZZANINE LAYOUT
109 | CT2B-K-1020 | VERTICAL TRANSPORTATION INSTALLATION - 2ND STOREY LAYOUT
110 | CT2B-K-1M20 | VERTICAL TRANSPORTATION INSTALLATION - 2ND STOREY MEZZANINE LAYOUT
111 | CT2B-K-1030 | VERTICAL TRANSPORTATION INSTALLATION - 3RD STOREY LAYOUT
112 | CT2B-K-1040 | VERTICAL TRANSPORTATION INSTALLATION - 4TH STOREY LAYOUT
113 | CT2B-K-1LR0 | VERTICAL TRANSPORTATION INSTALLATION - LOWER ROOF LAYOUT
114 | CT2B-K-0301 | VERTICAL TRANSPORTATION INSTALLATION - LIFT SUPERVISORY CONTROL PANEL, LIFT STOPPING CHART,LIFT HALL CALL BUTTON, LIFT BLOCK DIAGRAM & LIFT NETWORK SCHEMATIC DIAGRAM SYSTEM
115 | CT2B-K-0302 | VERTICAL TRANSPORTATION INSTALLATION - LIFT SCHEDULE
116 | CT2B-K-0401 | VERTICAL TRANSPORTATION INSTALLATION -EVACUATION/FIRE LIFT - EL01/FL01 & EL02/FL02 TYPICAL HOISTWAY AND LIFT MACHINE ROOM PLAN AND SECTION
117 | CT2B-K-0402 | VERTICAL TRANSPORTATION INSTALLATION - SERVICE LIFT (SL01) TYPICAL HOISTWAY AND MACHINE ROOM PLAN AND SECTION
TELECOMMUNICATIONS INSTALLATION
118 | CT2B-T-0001 | TELECOMMUNICATIONS INSTALLATION- SITE & LOCATION PLAN
119 | CT2B-T-1B10 | TELECOMMUNICATIONS INSTALLATION- BASEMENT 1 LAYOUT
120 | CT2B-T-1010 | TELECOMMUNICATIONS INSTALLATION- 1ST STOREY 1 LAYOUT
121 | CT2B-T-1M10 | TELECOMMUNICATIONS INSTALLATION- 1ST STOREY MEZZANINE LAYOUT
122 | CT2B-T-1020 | TELECOMMUNICATIONS INSTALLATION- 2ND STOREY LAYOUT
123 | CT2B-T-1M20 | TELECOMMUNICATIONS INSTALLATION- 2ND STOREY MEZZANINE LAYOUT
124 | CT2B-T-1030 | TELECOMMUNICATIONS INSTALLATION- 3RD STOREY LAYOUT
125 | CT2B-T-1040 | TELECOMMUNICATIONS INSTALLATION- 4TH STOREY LAYOUT
126 | CT2B-T-1LR0 | TELECOMMUNICATIONS INSTALLATION- LOWER ROOF LAYOUT
127 | CT2B-T-0301 | TELECOMMUNICATIONS INSTALLATION- MDF ROOM, TYPICAL RISER LAYOUT, SECTIONS, DETAILS, AND SINGLE LINE DIAGRAM
128 | CT2B-T-0302 | TELECOMMUNICATIONS INSTALLATION- TELECOM RISER LAYOUT, SECTION & 3D VIEW
22KV/LV SUBSTATION
129 | CT2B-E-8100 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : SITE & LOCATION PLAN
130 | CT2B-E-8101 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION :1ST STOREY PLAN
131 | CT2B-E-8102 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : BASEMENT 1 PLAN
132 | CT2B-E-8103 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : INCOMING CABLES SECTIONS
133 | CT2B-E-8104 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : SWITCHROOM, CABLE CHAMBER LAYOUT PLAN
134 | CT2B-E-8105 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : SWITCHROOM, CABLE CHAMBER SECTION & ELEVATION
135 | CT2B-E-8106 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : LIGHTING, POWER LAYOUT, SINGLE LINE DIAGRAM AND STANDARD DETAILS
136 | CT2B-E-8107 | ELECTRICAL INSTALLATION- 22KV/LV SUBSTATION : NOTES AND STANDARD DETAILS